Project Review
LunchAround
June Ist, 2011
Lorenzo Bovio
Francesco Bronzino
Davide Concas

---
Project Review
Agenda:
  - Project goals
  - User stories – use cases – scenarios
  - Original Project plan summary
  - Status as of May 30th 2011
    - Analysis and Design
    - Spikes
    - Coding
    - UI and user interaction draft (on paper or ...)
  - Updates to the project plan

---
Project goals
- Create a communication platform between clients and restaurateurs.
- Our service will let to:
  - Make searches of restaurants by using user location, kind of food and other types of filters.
  - Visualize restaurants datas and the daily menus.
  - Review a restaurant.
  - Receive recommendations possibles liked restaurants.
- Principal social networks interaction.
- Access from various platforms.

---
User stories
- Daily the manager setup his menu:
  - The manager login to the service
  - A page offer the possibility to insert new dishes and to assign them a category and a price.
  - When the manager begin typing the system suggest him old dishes already inserted before.
  - The manager assign to the menu a validity.
  - The system save the menu(every dish insertion).
  - The system redirect the manager to his own personal page.

---
User stories
- A registered user review a restaurant:
  - The user search the restaurant that he is looking to review.
  - The system check that the user is already logged in.
  - If the user has already reviewed the restaurant he will have the possibility to change it.
  - The user review the restaurant filling out the relative form.
  - The system store the review and the user preferences.

---
Original Project plan summary
- Analysis(discuss DB schema, define data dictionaries, object-oriented analysis, CRC cards): 5 weeks
- Design(define modules and interfaces, map web pages, specify APIs for other groups interaction): 2 weeks
- Spikes(Twitter, Facebook, Maps...): 3 weeks
- Development: 6 weeks
- Test: continuos tests + 1 final week

---
Status as of May 30th 2011
- Analysis: completed.
- Design(define modules and interfaces, map web pages, specify APIs for other groups interaction): complete the specification of the APIs
- Spikes:
  - Completed: Twitter, Facebook, JSF.
  - Not completed: Maps, Directions,Buzz.
- Development: ejb and relative facades

---
Updates to the project plan
- Added interaction with Google Directions.
- Added interaction with Google Buzz.
- Development time extended from 6 to 8 weeks (because of new interactions and related spikes).

---
Thank you for your attention !
Questions?